PowerEnJoy
PP
Project Plan

# Introduction

## Purpose
The goal of this document is to describe the schedule adopted in the development process of PowerEnJoy. The document will also show the criteria used to estimate the total cost and effort of the project. The task division is enlisted in the second part of the document as well as the resource assignment to each task.

## Scope
PowerEnJoy provide car sharing to its users by using a mobile application for the user and an administration system to manage the cars involved and the related issues.
The system allow the users to search and reserve a car located in specific safe areas in which the user is encouraged to park once his trip is over. To allow a user to benefit from the service the system provide a registration and login service. In addiction to this PowerEnJoy offers a series of advantages to reduce the fee required to encourage the user to respect the environment.
PowerEnJoy is a software solution which comes new in the market, moreover it represent a quite complex system since it has to communicate with different external entities (central system and cars).

## Definitions, acronyms and abbreviations
In this document several keywords are presented which may have a special meaning and definition. They are as follows:
- RASD: Requirements analysis and definition document.
- DD: Design document.
- FP: Function Points.
- COCOMO: Contructive Cost Model.
- ILF: Internal Logic File
- ELF: External Logic File.
- SLOC: Source Lines Of Code.

## References
- RASD available on the GitHub page of the group.
- DD available on the GitHub page of the group.

Cost and effort estimation

Function points
To estimate the complexity and dimension of the project we used function points which are assigned to each functionality[1] of the system based on the complexity it presents.
[1] The functionalities shown in the table are coherent to the one described in the RASD

Type	Functionality	Complexity	FP
ILF
	user location	simple	7
	reservation	medium	10
	trip	medium	10
ELF
	safe area	medium	7
	car	complex	10
	reservation[2]	medium	7
	user	simple	5
External Input
	login	simple	3
	logout	simple	3
	registration	medium	4
External Output
	find safe areas	simple	4
	find car	simple	4
External Inqueries
	reserve car	complex	6
	open car	medium	4
	start car	medium	4
	leave car	complex	6
Total			94
[2] Notice that the reservation is stored both in the internal storage and in the central system external to ours.

COCOMO 2
To evaluate the cost and effort corresponding to the FPs and our team and project qualities we use COCOMO2. The level assigned to each driver reflect the project described in the previous documents and the nature of our team.

Type of Driver	Driver	Level
Software Scale Drivers
	Precedenteness	Low
	Development Flexibility	Nominal
	Architecture/Risk Resolution	High
	Team Cohesion	High
	Process Maturity	Low
Software Cost Drivers
Product
	Required Software Reliability	High
	Data Base Size	Nominal
	Product Complexity	High
	Developed for Reusability	Nominal
	Documentation Match to Lifecycle Needs	Nominal
Personnel
	Analyst Capability	Nominal
	Programmer Capability	Nominal
	Personnel Continuity	Nominal
	Application Experience	Low
	Platform Experience	High
	Language and Toolset Experience	High
Platform
	Time Constraint	Very High
	Storage Constraint	Nominal
	Platform Volatility	Low
	Project Use of Software Tools	Nominal
	Multisite Development	Nominal
	Required Development Schedule	Nominal

Results:
Effort: ~27 Person-month
Total Equivalent Size: ~5000 SLOC
Task division and Resources allocation

In the following we show the plan of the project as a list of tasks and subtasks that cover the main activities required to implement the system. Each task has a starting and ending date and it is assigned to one or more members (U, S, R stands for Ulvi Ismayilov, Saeed Ektesabi and Riccardo Campo).

Task	Subtask	Assigned to	Starting date	Ending date
RASD[3]		U, S, R	17/10/16	04/11/16
	Initial requirements elicitation	S, R	17/10/16	28/10/16
	Initial requirements modelling	U, S	24/10/16	04/11/16
DD		U, S, R	07/11/16	25/11/16
	Architecture design	U, R	07/11/16	18/11/16
	Alghoritms	U, S	14/11/16	25/11/16
	Mockups	S, R	21/11/16	25/11/16
Development		U, S, R	28/11/16	10/03/17
User management		U, R	28/11/16	16/12/16
	Registration	R	28/11/16	02/12/16
	Login	U	28/11/16	02/12/16
	Account management	U, R	05/12/16	16/12/16
API communicator		S	28/11/16	05/01/17
	Initial implementation	S	28/11/16	16/12/16
	Securing and optimizing	S	19/12/16	05/01/17
Trip management		U, S, R	19/12/16	03/02/17
	Reservation management	U, S	16/01/17	03/02/17
	Map implementation	S, R	19/12/16	13/01/17
UI design		U, S, R	06/02/17	10/03/17
	Initial design	U, S	06/02/17	24/02/17
	Wireframing	U, R	20/02/17	09/03/17
	Graphic design of icons and buttons	U	06/03/17	10/03/17
Testing		U, S, R	28/11/16	12/05/17
	Constant testing	U, S, R	28/11/16	10/03/17
	Unit testing	U, S, R	13/03/17	14/04/17
	Solving bugs	U, S, R	17/04/17	12/05/17
Final operations		U, S, R	15/05/17	16/06/17
[3] Note that both the requirements and the design is subject of change during the whole development process, so it may be necessary to update the documents

The diagram below helps visualize the tasks in the timeline of the project.

Risks
The following table describes the risks, their impact on the project and possible actions that can be take in order to react to these possible events.

P- Probability, I – Impact, E – Exposure of Risks
Ranking is done due to ---> E (Exposure of Risks) = P (Probability) x I (Impact)

Rank	Risk Definition	P	I	Action
4	Little experience in group-working	moderate	marginal
1	Issues appearing in complex systems involving cars	moderate	catastrophic
9	Communication issues with central system	low	critical	Improve the communication with the old system hiring a member from the old system development team
5	Key staff are ill at critical times in the project.	low	catastrophic	Reorganize team so that there is more overlap of work and people therefore understand each other’s jobs.
10	Changes to requirements that require major design rework are proposed	low	marginal
8	The organization is restructured so that different managers are responsible for the project	moderate	marginal
2	The database used in the system cannot process as many transactions per second as expected	moderate	catastrophic	Investigate the possibility of buying a higher-performance database.
3	Change of the city government	moderate	critical	Organize meeting with the new government representatives to clarify the changes in the municipal laws
7	Wrong selected city in terms of market demand	low	catastrophic	Try to adapt the current system to an eventual new target city.
6	Organizational financial problems force reductions in the project budget.	low	catastrophic	Prepare a briefing document for senior management showing how the project is making a consistent contribution to the goals of the business and presenting reasons why cuts to the project budget would not be cost-effective.

Hours of work

Team member	Hours
Riccardo	5
Saeed	4
Ulvi	4

Meetings	4

Changelog

Version	Date	Comment
1.0	22/01/2017	Release
1.1	31/01/2017	Extended task division part